## Wooooo
Module | Sub Module | Description | Current Status | Plan
View | Login View |  | In development
| Begin View | Let user to select ist roller: slave or master | In development
| Master View | Used in Master roller, can check the position of others | In development | Should be change its name to Master View
| Slave View | Used in Slave roller
Controler | Communication
Model | User
System Archtecture | Shall we seperate the two roller between Slave and Master?
GitHub | Sign Up | [9/28/2014] Get the account from GitHub and try to create a respository during the Windows client. Connection created sucessfully between the local workspace and GitHub respository. The GitHb can only connect to the GitHub folder of the local computer. So copy the project to GitHub folder.
Slave | Login View | [9/27/2014] Create the first project in Android Studio Begin to build the first software version for Slave | [9/28/2014] Change the min required version of sdk to 11 in order to use the above property. Can't use style/Theme.Holo.NoActionBar as the theme of LoginActivity. The reason is unknown.
| Communication | [9/27/2014] Try to integrate XMPP message into the SW. Maybe need support from Google App Engine
| Google App Engine | [9/27/2014] A sample project should be created during the totorial
| Model | [9/28/2014] Create UserData.
| Begin View | [9/30/2014] Create an adpter view to combinate the Slave and Master modes. -Press "I'm coming" to go to the slave mode; -Press "I'm waiting" to go to the master mode.

## Black Knowledge
Topic | Date | Description
Change the min or max requried sdk version | 2014-09-28 | These two properties could be changed in build.gradle
android.os.AsyncTask | 2014-09-28 | doInBackground must be implemented with an ARRAY as input parameter